## Project Plan and Gantt
Project Name | QuanLyCuaHangDoChoi
Project Manager | Võ Minh Tú
Project Deliverable
Scope Statement:
Start Date | 2016-08-19
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Team | 2016-08-20 | 2016-08-20 | 0 | Complete
Agree on objectives | Team | 2016-08-21 | 2016-08-21 | 0 | In-progress
Detailed Reqs. | Team | 2016-08-22 | 2016-08-25 | 3 | Overdue
Techincal Reqs. | Team | 2016-08-25 | 2016-08-27 | 2 | Not started
DB Development | Pham Văn Thiện | 2016-08-27 | 2016-09-01 | 5 | Not started
Connect DB | Võ Minh Tú | 2016-09-01 | 2016-09-04 | 3 | Not started
Insert/Update/Query | Team | 2016-09-05 | 2016-09-11 | 6 | Not started
API Development | Võ Minh Tú | 2016-09-12 | 2016-09-19 | 7 | Not started
Function 1 | Võ Minh Tú | 2016-09-20 | 2016-09-23 | 3 | Not started
Function 2,… | Phạm Văn Thiện | 2016-09-20 | 2016-09-23 | 3 | Not started
UI Client | Team | 2016-09-24 | 2016-09-27 | 3 | Not started
Testing | Team | 2016-09-28 | 2016-09-30 | 2 | Not started
Dev. Complete | Team | 2016-10-01 | 2016-10-04 | 3 | Not started
Hardware Config. | Team | 2016-10-05 | 2016-10-07 | 2 | Not started
System Testing | Team | 2016-10-08 | 2016-10-09 | 1 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Võ Minh Tú | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document 6. Design GUI/database. | minhminhtu96@gmail.com
Phạm Văn Thiện | Developer | 1. Design GUI/database. 2. Code. 3. Test 3. Analysis & design the system. | phvth3@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team